## MAIN
Date: | Description | Hours
January 16th 2023 | Worked on title screen a bit, set up tile maps, did sprite work, set up first movement script and animations. There is now and island and a working player with movement animations. | 6
January 17th 2023 | Added sound effects for walking on dirt and grass, also added colliders to character and tilemap itself. | 2
January 18th 2023 | Added bushes, 3 types: Rasberry, Blackberry, Blueberry. The bushes randomly generate with those 3 types of berries. Then every 200 seconds, they regenerate again. Also set up a system that detects which berry you're picking when you click the "interact" button | 5
January 19th 2023 | Added sprites for UI buttons, also started creating an inventory for the player. | 1
January 20th 2023 | Added binary file saving system for safe storage of data. This stores the amount of berries currently. | 1
January 21st 2023 | Started creating new sprites for inventory and use button. Did some planning for the inventory. | 1
January 22nd 2023 | Created most of the inventory system. When you get a berry it now adds it to your inventory. Took me 4 hours to fix an issue for the berries getting added to inventory. Realized it was because of a capital letter I. Coding sucks. | 7
January 23rd 2023 | Ran into a lot of bugs when trying to make the inventory save. There are so many things that aren't working but I'll get them fiugred out eventually. Made the health bar graphics though woohoo. | 2
January 24th 2023 | More bug fixing, fixed the big issue, now just have to figure out some data saving issues. | 2
January 25th 2023 | A little more bug fixing, still working on data saving. Started making graphics for hunger bar. | 1
January 26th 2023 | Guess what? MORE BUG FIXING WOOOO. Finally got the data saving to work correctly, feels good to be able to check that off my list. Still have a lot of things to tidy up, but we're making progress. | 1
January 28th 2023 | Hunger bar is now fully functional with built in decay. | 1
January 29th 2023 | Water bar fully functional and working. Also made hunger decay slower. Started working on daylight cycle system. | 2
January 30th 2023 | Worked a bit more on daylight cycle, running into a lot of lighting issues, hopefully I can figure them out. Also started scripting and designing the "use" button in the inventory. This will be used to eat berries and drink water, and probably other functionality. | 2
January 31st 2023 | Worked on the consume button for inventory items. Finally got a working system, now just have to implement it. | 1
February 1st 2023 | Consume button is finished and working completely. Items can now be stacked in inventory, you can eat all 3 types of berries. They give you a little bit of hunger replenishment and and tiny tiny bit of water replenishment. Also got the light cycle to work, I'm tweaking it a little bit , but overall very solid work day. | 2
February 2nd 2023 | Worked on daylight cycle system a little more, fixing some stuff up, also made the water delpletion a little slower and hunger depletion a slight bit faster. | 1
February 3rd 2023 | Fixed daylight cycle, 1200 second (20 minute) days, saves your current time and sunlight. Fixed an inventory issue where berries wouldn't dissapear when eating them. Berries now make a sound when you eat them. | 2
February 4th 2023 | Expanded the map, added more grass and bushes, fixed an error in the daylight cycle. | 1
February 5th 2023 | Added a day counter feature. Also fixed a small bug where the day number wouldn't update when you loaded in to the game. | 1
February 6th 2023 | Added water and the animations for the water, started adding the sound but it was being glitchy | 2
February 7th 2023 | School is taking a lot of my time away from this project, but I'm grinding it out, tried to fix the water bug but couldn't figure it out | 1
February 8th 2023 | Fixed the water bug, it was an animated tile issue. Lets gooooo. | 1
February 10th 2023 | Designed the sprite sheet for the character swimming animation. I think it looks decent but I'll have to see when I implement it tomorrow. | 1
February 11th 2023 | Looked around and tried to figure out the swimming animation, ran into some issues. | 1
February 12th 2023 | More of the same from yesterday, couldn't find a way to implement the animations into different senarios. | 1
February 13th 2023 | Put the swimming animation on the backburner, worked on being able to drink the water, some of it is just psuedocode, but some of it is functional. | 1
February 15th 2023 | Finished the swimming animation and started working on finishing the side effects that happen when you drink river water | 2
February 16th 2023 | Thought about a few ways I can start working on polishing the water drinking system for the river/water spots | 1
February 21st 2023 | Alright back after a long reset and weekend. Hoping to make some progres this week. Today I worked on the messages that pop up when you drink river water, also I started creating a hint/tip system. | 1
February 22nd 2023 | Finished off the functionality of the tip system, also now when you lose hunger or water it slows down the speed of the character. Also fixed a bug where your hunger or water could still go below 0 when you got river water side effects | 1
February 23rd 2023 | Added more water tiles throughout the map. Fixed the way to check if the user has played before. (This is used to display tips to newer players.) Also implemented a system to deplete your hunger and water faster if you are running. You lose more the faster you are going. If you are at a standstill, you will lose the base amount. I might change the base amount to be much lower though. | 2
February 27th 2023 | Created the tree, and also created the animation for the tree (currently it's like dancing so it needs some fixing). Tomorrow I will work on fixing the animation and adding some functionality. | 1
March 2nd 2023 | Fixed the tree animation, started making sand and gave it a sound effect when walking. | 2
March 7th 2023 | Worked on making a system to cut down trees and get wood. Right now you can collect wood and see it in your inventory, but it doesn't do anything yet. | 1
March 8th 2023 | Fixed the health system and the wood glitch that would happen when you could collect wood while swimming in water. Also started making the tree dissapearing system when you chop it down. | 1
October 4th 2023 | Well, we're back. After a very very long break from game design, I sharped up my programming skills and am ready to continue this project, here we go. Today I made the decision that this game will by a hybrid adventure/puzzle game. I made the dungeon room and started incoorperating new textures. (Not marking break days anymore) | 1
October 11th 2023 | I added walls that have collision effects so you can't run outside the map. Also added tips that guide the player through the dungeon part of the game. | 1
January 20th 2024 | Back again woohooooo. Hopefully can make some actual progeress this month. I worked on extending the dungeon part of the map and brainstorming new ideas for the puzzle part of the game. | 1
February 5th 2024 | Started working on the dungeon door mechanic, now I have a system to detect which door the user is interacting with by checking the position the door is on the map. Next I need to design a way to unlock the doors. | 1
February 12th 2024 | Grinded today, took me forever to get the random chest generation working but I got it. | 3
Feburary 13th 2024 | Made the chest generation more realistic and mandated the amount of chests that spawn | 1
July 22nd 2026 | Cleaned up some OLD code. Made the add/remove item a broad function with parameters instead of an individual function for each berry. Also kinda fixed the bug where the character would swim on land when close to water. The character does this less far away from the water now, can probably still fix this more by making more of the hitbox required to be touching. | 1
July 23rd 2026 | Cleaned up the map a bit, one of the sides was uneven and it was annoying me. Scrolled through some code for a bit to refamiliarize myself with my own code lol. Started working on chest generation again. There seems to be a glitch in the saving function that doesn't save the inventory when berries are eaten apparently? | 2
July 27th 2026 | Finished chest generation, currently have 10 chests generating throughout the map randomly, might change this. Also might add different rarities of chest perchance? Still need to fix the inventory not saving bug. | 2
July 28th 2026 | Created chest UI and some logic for opening the chests, doesn't work yet with the use button, will fix. Fixed not saving bug. | 2
August 13th 2026 | Added new assets/sprites and implemented a opacity-changing system for the interact button based off of interactability. (Some bugs) | 2
August 14th 2026 | Added the new inventory slot graphic to the chest UI, also the inventory background UI was implemented for chests. Working on fixing a few bugs. | 3
CURRENT TOTAL HOURS |  | 82